## CITSmart FDM Controls
CITSmart Fast Deployment Methodology (FDM)
Item | Phase | Step | Action/Actors | Objectives | Input Control | Output Control | Status | Observations
1. | Organizational Change Management
| Prepare | Mapping key users | Action: Mapping user keys Actors: Project team | 1 - Identify the key users (target audience) that will be impacted by the implementation of the new service management system. | 1 - Information collected with the project team. | 1 - Target audience for change.
|  | Mapping scenarios | Action: Map the current and future scenario Actors: Project Team | 1 - Identify the changes in how things are done without the new system and how they will be made after the change. 2 - Identify critical points that can bring resistance and mitigation actions. | 1 - Information collected with the project team. | 1 - Mapped change scenarios 2 - Critical points and actions to mitigate identified problems.
|  | Creating Organizational Change Management Plan | Action: Develop organizational change plan Actors: Project Team | 1 - Define and plan the actions needed to engage and involve the users of the new system. 2 - Formalize the organizational change plan using all the information and artifacts generated in the previous steps. | 1 - Information generated in previous steps. | 1 - Organizational change plan elaborated and approved.
| Execute | Deployment of the change plan | Action: Execute the organizational change plan. Actors: Project Team and Stakeholders. | 1 - Execute the actions of the organizational change plan. | 1 - Change plan approved | 1 - Updated change plan. 2 - Evidence of the execution of the change plan.
| Evaluate | Evaluating the effectiveness of the change plan | Action: Evaluate execution of the organizational change plan. Actors: Project Team and Stakeholders. | 1 - Evaluate the effectiveness of the organizational change plan in order to detect possible failures or distortions in the actions carried out. 2 - Documenting failures and, if appropriate, undertaking due treatment in the next step of the organizational change process. | 1 - Updated Change Plan. | 1 - Evaluation registration of the organizational change plan, indicating the failures and distortions that must be met by priority.
| Correct and Refine | Correcting and refining failures and distortions that impact on change | Action: Correct failures and distortions of the organizational change plan. Actors: Project Team and Stakeholders. | 1 - Correct identified and forwarded failures and distortions for treatment in the previous step. Corrections/improvements should be made available to stakeholders. | 1 - Evaluation registration of the organizational change plan, indicating the failures and distortions that must be met by priority. | 1 - Failures and distortions treated.
2. | Communication
| Prepare | Establishing Communication Channels | Action: Define official project communication channels Actors: Project Team | 1 - Formalize the official communication channels of the project. | 1 - Information collected with the project team | 1 - Defined communication channels
|  | Mapping actors | Action: Mapping communication actors Actors: Project Team | 1 - Map communication, speaker and receiver actors - main and substitute. All stakeholder contacts should be kept current and shared with the project team. | 1 - Information collected with the project team | 1 - Mapped Process Actors
|  | Building the Communication Matrix | Action: Create communication matrix Actors: Project Team | 1 - Create communication matrix: map the main subjects to be informed, expected actions/objectives, who is responsible for sending and who should receive the information (audience), by what means, at what frequency and what product can be generated (example: meeting minutes, requirements gathering minutes, status report, alert report) 2 - Formalize/disseminate communication matrix. | 1 - Information collected with the project team | 1 - Elaborated communication matrix.
|  | Preparing the Communication Plan | Action: Develop communication plan Actors: Project Team | 1 - Define and plan the actions necessary to ensure effective communication for all stakeholders. 2 - Formalize the communication plan, using all the information and artifacts generated in the previous steps. | 1 - Communication Matrix. | 1 - Communication plan elaborated and approved
| Execute | Deploying the Communication Plan | Action: Execute the communication plan. Actors: Project Team and Stakeholders. | 1 - Execute the communication plan at all stages of the deployment project. | 1 - Approved communication plan. | 1 - Updated communication plan. 2 - Evidence of the execution of the communication plan.
| Evaluate | Evaluating the effectiveness of project communication | Action: Evaluate execution of communication plan. Actors: Project Team and Stakeholders. | 1 - Evaluate the effectiveness of the communication plan in order to detect any failures or distortions in the communication applied throughout the project. 2 - Document failures and, if appropriate, perform due treatment in the next step of the communication process. | 1 - Updated communication plan. | 1 - Evaluation registration of the communication plan, indicating the failures and distortions that should be treated with priority.
| Correct and Refine | Correcting and refining communication failures and distortions | Action: Correct communication plan failures and distortions. Actors: Project Team and Stakeholders. | 1 - Correct identified and forwarded failures and distortions for treatment in the previous step. Corrections/improvements should be made available to stakeholders. | 1 - Evaluation registration of the communication plan indicating failures and distortions that should be treated with priority. | 1 - Failures and distortions treated 2 - Communication plan versioned and updated.
3. | Phase of the Deployment Project
3.1 | Prepare/Plan | Understanding the Context | Action: Promote internal transition meeting. Actors: Business team and project team. | 1 - To pass on all the knowledge about the project and about the customer acquired throughout the commercial process. 2 - Forward all relevant documentation to the technical team. 3 - Identify Stakeholders. 4 - Identify project risks | 1 - Information capture document (Workbook - Technical Discovery). 2 - Commercial proposal or contract. 3 - Emails or other relevant communication artifacts. | 1 - Proposal of the Project Plan
|  | Promoting the kickoff meeting | Action: Promote KickOff meeting. Actors: Business team, project team. | 1 - Present and approve the Project Plan, elaborated from the understanding of the context; 2 - Present Project Deployment Team (Provider); 3 - Orient the client on the strategies of communication and CMO (Organizational Change); 4 - Align / Equalize expectations, especially deadlines; 5 - Display / Adjust macro timeline; 6 - Define critical needs; 7 - Present deployment strategy, including mapped risks to date and quick-wins | 1 - Initial proposal of the Project Plan, containing scope and non-scope, risks and restrictions mapped so far, and macro schedule. | 1 - Meeting Registration. 2 - Validated Project Plan.
|  | Preparing the Project Plan | Action: Prepare final version of the Project Plan. Actors: Project team. | 1 - Finalize the Project Plan: Presentation and documentation of the main features of the client's business and how the CITSmart solution will be implemented to meet the contracted scope. | 1 - Validated Project Plan | 1 - Project Plan approved.
| Perform | Raising technical requirements | Action: Promote Technical Meeting for" Workbook - Technical Discovery " Actors: Technical Project Team (Client and Provider) | 1 - Map technical requirements for configuration and customization of the CITSmart platform. | 1 - Document of capture of technical information (Workbook - Technical Discovery). | 1 - Workbook - Technical Discovery completed according to customer requirements and approved.
|  | Configuring and customizing the CITSmart Platform | Action: Make customizations and configurations in the Solution according to information in the Workbook - Technical Discovery. Segment the macro schedule into smaller delivery cycles, according to priority items for the solution sold. Carry out the adjustments requested by the customer, after homologation of partial deliveries. Actors: Technical team of project. | 1 - Configure and customize the CITSmart Platform: it is in this step that the registers are inserted into the system, either by importing the legacy system or by insertion by the consultants / users. It is in this step that flow automations, dynamic form creation and integrations are performed. | 1 - Macro Schedule 2 - Workbook - Technical Discovery completed according to client's requirements and approved. 3 - Adjustments requested by the customer after homologation of partial deliveries | 1 - Platform modules configured according to requirements survey or points for customer approval.
|  | Homologating partial deliveries | Action: Homologate the delivered functionality. Actors: Technical project team (partner and / or manufacturer) and client | 1 - Obtain clients feedback regarding the features developed in each delivery cycle. 2 - Prioritize the necessary adjustments to be made. 3 - Perform partial delivery tests. | 1 - Modules of the CITSmart Platform configured according to the requirements survey. 2 - Script of tests. | 1 - Script of tests. 2 - Request for change (when change scope, term or budget). 3 - Customer acceptance for each delivery cycle, including possible points of adjustment requested.
|  | Homologating the solution | Action: Homologate the complete solution. Actors: Technical project team (partner and / or manufacturer) and client | 1 - Perform integrated tests. Here it is guaranteed that it is possible to make the system available in production (Go Live). 2 - Make the necessary adjustments identified in the tests. | 1 - Scripts of test. | 1 - Test script completed. 2 - Final acceptance of the customer after making all the adjustments demanded.
| Capacitate | Training key users | Action: Train users. Actors: Training team (partner and / or manufacturer) and key client users | 1 - Perform training. Training key users is critical since they are the multipliers of knowledge in their teams | 1 - Menus by user profile. 2 - Didactic material. | 1 - Lists of participants signed. 2 - Training evaluation forms filled in.
| RollOut | Launch of the New Platform | Action: Promote marketing campaign and / or endomarketing. Actors: Project Team and Marketing Team | 1-Carry out a marketing and / or endomarketing campaign to launch the system in production, where they are informed: advantages of the new solution, access instructions, channels for clarifying doubts, among others. | 1 - Email marketing model. 2 - Model of institutional videos. 3 - Folders and / or other advertising pieces. | 1 - Advertising pieces disclosed in a timely manner.
| Go live | Going into Production | Action: Entry into production. Actors: Technical project team. | 1 - Prepare and release environment for entry into production. | 1 - Final acceptance document. | 1 - Final acceptance document signed by the client.
| Assisted Operation | Performing Assisted Operation | Action: Assisted Operation. Actors: Technical project team. | 1 - Perform the assisted operation. At this stage, the consultant usually watches the operation for thirty days, adjusting some unidentified points in the preparation and final stages, as well as supporting the users, who totally change their routine and are getting used to the new tool. | 1 - Monitoring document to the Assisted Operation. | 1 - Assisted Operation Document signed after completion of the operation (containing the adjusted items, if any).